## Sheet1
Project | Compet Care
Project Type | Mobile App
Test_Id_No | Module | Sub Module | Bug Summary | Suggestion | Severity | Priority | Status | Result | Screenshot | Date Of Testing | Open Date | Close Date | Dev Comment | QA Comment
TC_01 | Login | Login | When the OTP process starts, the OTP timer stops if the user performs other activities. In my view, once the OTP process starts, the timer should run continuously until it ends. |  | High | High | Open | Fail |  | 2026-02-04 | 2026-02-04
TC_02 | Home | Ask AI | In the Ask AI module, when the user clicks the camera button, the camera does not open. Additionally, camera permission is not requested at the time of app installation; instead, the app asks for camera permission only when the user tries to use the camera. |  | Critical | High | Open | Fail |  | 2026-02-04 | 2026-02-04
TC_03 | Home | Ask AI | The AI chatbot is operating quite slowly. When a user asks a question, the chatbot responds with a delay, and if the user asks another question, it sometimes returns the answer to the previous question. This needs to be checked. Share you a screenshot |  | High | High | Open | Fail |  | 2026-02-04 | 2026-02-04
TC_04 | My Profile | Shipping Address | The First Name, Last Name, City, and State fields should accept only alphabetic characters, but app currently allow numbers and special characters as well. |  | High | High | Open | Fail |  | 2026-02-04 | 2026-02-04
TC_05 | My Profile | Shipping Address | Phone Number should be accept 10 digit numbers only, but app currently allow numbers and special characters as well. |  | High | High | Open | Fail |  | 2026-02-04 | 2026-02-04
TC_06 | My Profile | Personal Details | The Phone Number field is not properly aligned. The mobile number is not clearly visible, as the alignment is centered. |  | Medium | Medium | Open | Fail |  | 2026-02-04 | 2026-02-04
TC_07 | My Profile | Profile Picture | When a user sets a profile picture, it appears correctly, but after pressing the back button, the profile picture becomes empty. | In the Profile Picture section, provide a camera option so that users can take a photo directly using the camera. | High | High | Open | Fail |  | 2026-02-04 | 2026-02-04
TC_08 | My Profile | My Pets | Pet Name fields should accept only alphabetic character. |  | Medium | Medium | Open | Fail |  | 2026-02-04 | 2026-02-04
TC_09 | My Profile | My Pets | There is no option to remove pets. When a user sells their pet and wants to remove the entry from My Pets, there is no remove option available. |  | High | High | Open | Fail |  | 2026-02-04 | 2026-02-04
TC_10 | My Profile | My Pets | Avatars are not available when adding data for Rabbits, Hamsters, Pigs, or Ferrets. |  | High | High | Open | Fail |  | 2026-02-04 | 2026-02-04
TC_11 | My Profile | My Pets | In the Pet Type field, if the user selects Other from the dropdown, the Add New Pet button is disabled. Since the Other option has no use, it can be removed from the Type dropdown. |  | High | High | Open | Fail |  | 2026-02-04 | 2026-02-04
TC_12 | My Profile | Shipping Address | When a user wants to make changes to an existing address, there should be an Update button instead of an Add button, since the user is only updating the address information. |  | Medium | Medium | Open | Fail |  | 2026-02-04 | 2026-02-04
TC_13 | Login | Login | When the user logs in with a mobile number, a toast message saying “OTP sent successfully” is displayed. The font size of this toast message should be increased. Increse a font size all toast msg. |  | Medium | Medium | Open | Fail |  | 2026-02-04 | 2026-02-04
TC_14 | Services | Veterinary | When the user clicks on Veterinary, a list of doctors and clinics is displayed. However, I want to highlight that some of these are far from my location, and the distances shown in kilometers are incorrect. The list should show doctors and clinics from nearby locations or my local area. |  | Critical | High | Open | Fail |  | 2026-02-04 | 2026-02-04
TC_15 | Services | Veterinary | If the user tries to book an appointment, it asks to select a time slot. However, no date or time slot options are available, so the user is unable to book the appointment. |  | Critical | High | Open | Fail |  | 2026-02-04 | 2026-02-04
TC_16 | Location | Location | After first-time login and granting location permission, the app displays an incorrect location. Example: current location is Thane, but the app shows Central Mumbai. Correct location appears only after manually using the Detect Location option. |  | High | High | Open | Fail |  | 2026-02-04 | 2026-02-04
TC_17 | Services | Sitters | When select Sitters and Pet Store option and go to seletc All then select Sitters, Pet store option is different. need to check this |  | Critical | High | Open | Fail |  | 2026-02-04 | 2026-02-04
TC_18 | Home | Comrehansive Pet Insurance | When the user clicks on Comprehensive Pet Insurance, data for all insurance companies is displayed; however, clicking the back button throws a ThrottleException error. This error is displayed continuously on screen |  | Critical | High | Open | Fail |  | 2026-02-04 | 2026-02-04
TC_19 | Home | Comrehansive Pet Insurance | When the user clicks on Comprehensive Pet Insurance, data for all insurance companies is displayed; however, when clicking the back button, it should open the home page, but instead it opens different pages. |  | High | High | Open | Fail |  | 2026-02-05 | 2026-02-05
TC_20 | Home | Comrehansive Pet Insurance | The insurance company page looks messy, and the logo is not properly aligned. | Logo is properly set |  |  | Not a Bug |  |  | 2026-02-05 | 2026-02-05
TC_21 | Home | Comrehansive Pet Insurance | For example, when the user clicks on ICICI Lombard Insurance, I experienced a scrolling issue where the page requires multiple scroll attempts before it scrolls properly. |  | High | High | Open | Fail |  | 2026-02-05 | 2026-02-05
TC_22 | Home | Wishlist | When the user adds a particular pet product to the wishlist, it is not added to the shopping wishlist. |  | High | High | Open | Fail |  | 2026-02-05 | 2026-02-05
TC_23 | Store | Store | Some product prices are missing. and below of the rupee symbol there is an option shows that 4 variants available; so, clicking on it displays the same product in the same color. Additionally, for clothing-related products, the unit is shown in grams, which is applicable to food products, not clothing. | Please see the recording | Critical | High | Open | Fail |  | 2026-02-05 | 2026-02-05
TC_24 | Store | Store | When the user clicks on the Medusa Shorts product and scrolls down to the Similar Products section, clicking on the Pedigree product should open the Pedigree product page, but it still displays the Medusa Shorts product. |  | High | High | Open | Fail |  | 2026-02-05 | 2026-02-05
TC_25 | Store | Store | When a user tries to buy the Medusa Shorts product and clicks the Add to Cart button, they only find out that the product is out of stock. This information should be shown on the product page so the user can understand immediately that the product is out of stock. |  | High | High | Open | Fail |  | 2026-02-05 | 2026-02-05
TC_26 | Store | Checkout | When user proceed to Payement, and any reason user back to the payment page somethin error is pop up on the page |  | High | High | Open | Fail |  | 2026-02-05 | 2026-02-05
TC_27 | Store | Catagories | When the user clicks on the Categories icon, the Toys, Treats, and Cloths pages open correctly, but the Bath, Grooming, and Medicines pages do not open. |  | High | High | Open | Fail |  | 2026-02-05 | 2026-02-05
TC_28 | Notification | Notification | A red dot appears on the notification icon to indicate that notifications are present, but when the user clicks on the icon, no notifications are displayed.” |  | High | High | Open | Fail |  | 2026-02-05 | 2026-02-05
TC_29 | Services | Dog Walking | Google Maps shows an incorrect location when a user selects a vendor (e.g., Paws & Perfection Pet Spa, Kharghar, Navi Mumbai) from the vendor list. |  | High | High | Open | Fail |  | 2026-02-05 | 2026-02-05
TC_30 | Store | Store | The cart indicator is displayed when the cart is empty; however, it does not appear after a product is added to the cart. | Please see the recording | High | High | Open | Fail |  | 2026-02-05 | 2026-02-05
TC_31 | Checkout | Checkout | In the Checkout page, pressing the plus (+) button to increase product quantity works up to 6 or 7, then the count resets to 2. Needs investigation. | Please see the recording | High | High | Open | Fail |  | 2026-02-05 | 2026-02-05
TC_32 | Home | Adop a Furry Friend | Some items in the “Reason for Adoption” dropdown are nested inside each other when adding a pet for adoption. |  | High | High | Open | Fail |  | 2026-02-05 | 2026-02-05
TC_33 | Home | Adop a Furry Friend | The Vaccination field is disabled when adding a pet for adoption, preventing user selection. |  | High | High | Open | Fail |  | 2026-02-05 | 2026-02-05
TC_34

## Sheet2
Severity | Priority | Status | Result
Critical | High | Open | Pass
High | Medium | Closed | Fail
Medium | Low | Re-open
Low |  | Not a Bug

## Sheet3
Test Report
Issue Type | Open | Fixed | Re-Open | Not-bug | Close | Under Observation
Critical | 0 | 0 | 0 | 0 | 0 | 0
High | 0 | 0 | 0 | 0 | 0 | 0
Medium | 0 | 0 | 0 | 0 | 0 | 0
Low | 0 | 0 | 0 | 0 | 0 | 0
Suggestion | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 0 | 0

## Sheet4
Sr. No. | Department | Product Name | Application Type (Web, Mobile, Windows, API) | No. of Test Cases | No. of Pages / API
1 | Digi Banking | IMPS | API | 10 | 2
2 |  | UPI
3 |  | NETC
4 |  | Agency Banking
5 |  | Carde Portal
6 |  | Wallet
7 |  | Trace
8 |  | Kiosk
9 |  | CMS Portal
10 |  | ATM
11 |  | Android
12 |  | IOS
13 |  | Kiosk | Windows | 200 | 30
14 | Monitoring | Managecall | Web | 35 | 3
15